## Status
SIGN AUTOMATION STATUS SCRIPTING: OAT APP-ITERATION4 | [7 empty] | Date : 09/13/2018 7:00 PM IST
[7 empty] | Overall Status |  | Green
SUMMARY: • Below Functional Area table contains test cases planned for OAT Application Iteration 4
# | Issue Description | [5 empty] | Script Blocked |  | Owner | Status
1 | Certs Scenarios cannot be taken up due to control issue | [5 empty] | 22 |  | Onshore | Open
2 | Vivint Skus WF is not setup correctly | [5 empty] | 27 |  | Onshore | Open
3 | REPL is not working | [5 empty] | NA |  | Onshore | Open
4 | Dotcom orders are not reaching STH | [5 empty] | 5 |  | TDM | Open
SUMMARY BY FUNTIONAL AREA:
| Functional Area | Total Planned | Automated | Blocked | Not Started | %Completion
| Product Variations-Swatch | 14 | 6 | 0 | 8 | 100
| Services-TTS-BBY Logo | 2 | 2 | 0 | 0 | 100
| Bundle & Save+GC+Tender | 0 | 10 | 0 | 0 | #DIV/0!
| Services | 10 | 0 | 0 | 10 | 0
| Total | 16 | 16 | 0 | 0 | 100
SCRIPTING PROGRESS

## Data
Test Plan Name | All
Point Count Trend | Column Labels
Row Labels | Blocked | In Progress | Never Run | Passed | Grand Total
\18.2 Automation Scripting\Apple Watch |  | 0 | 0 | 13 | 13
\18.2 Automation Scripting\Competitor Price Match | 1 | 0 | 9 | 113 | 123
\18.2 Automation Scripting\CPH | 1 | 0 | 14 | 67 | 82 | Functional Area | Total Planned | Automated | Blocked | Not Started | %Completion
\18.2 Automation Scripting\Mobile Returns |  | 1 | 4 | 53 | 58 | Product Variations-Swatch | 14 | 14 | 0 | 0 | 100
\18.3 & 18.4 Automation Scripting\18.3 : Home Security Services (Vivint) |  | 0 | 27 | 5 | 32 | Services-TTS-BBY Logo | 2 | 2 | 0 | 0 | 100
\18.3 & 18.4 Automation Scripting\18.3 : Link between GSP and Product is Broken\18.3 : Link between GSP and Product is Broken (Existing) |  | 0 | 5 | 1 | 6 | Bundle & Save+GC+Tender | 0 | 0 | 0 | 0 | #DIV/0!
\18.3 & 18.4 Automation Scripting\18.3 : Link between GSP and Product is Broken\18.3 : Link between GSP and Product is Broken (Misc) |  |  | 21 | 1 | 22 | ESL Pair By Planogram | 0 | 0 | 0 | 0 | 0
\18.3 & 18.4 Automation Scripting\18.3 : Link between GSP and Product is Broken\18.3 : Link between GSP and Product is Broken (Next Day) |  |  | 43 |  | 43 | Services | 0 | 0 | 0 | 0 | 0
\18.3 & 18.4 Automation Scripting\18.3 : Link between GSP and Product is Broken\18.3 : Link between GSP and Product is Broken (Order Mod) |  |  | 20 |  | 20 | Product Finder | 0 | 0 | 0 | 0 | 0
\18.3 & 18.4 Automation Scripting\18.3 : My Best Buy Program Transformation (MyBBY 3.0) |  |  | 44 |  | 44 | ESL Pair/Unpair-SES | 0 | 0 | 0 | 0 | 0
\18.3 & 18.4 Automation Scripting\18.3 : Return Avoidance - Customer Comment Capture | 1 | 0 | 11 | 39 | 51 | ESL Pair By Planogram-SES | 0 | 0 | 0 | 0 | 0
\18.3 & 18.4 Automation Scripting\18.3 : SimCard Bundle Breakage |  | 0 | 21 | 27 | 48 | Totals | 16 | 16 | 0 | 0 | 100
\18.3 & 18.4 Automation Scripting\18.3 : Vault - Price Override Parameters |  | 1 | 3 | 45 | 49
\18.3 & 18.4 Automation Scripting\18.4 : Prompt Refactoring |  |  | 27 |  | 27
\18.3 & 18.4 Automation Scripting\18.4 : Tax Exempt Customer Card\18.4 : RPROP & Energy Star |  |  | 22 |  | 22
\18.3 & 18.4 Automation Scripting\18.4 : Tax Exempt Customer Card\18.4 : TEC Changes |  |  | 60 |  | 60
Grand Total | 3 | 2 | 331 | 364 | 700

## Progress Trend
| __ | 2018-09-06 | 2018-09-07 | 2018-09-10 | 2018-09-11 | 2018-09-12 | 2018-09-13 | 2018-08-09 | 2018-08-10 | 2018-07-12 | 2018-07-13 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-11-21 | 2017-11-22 | 2017-11-23
Planned | 0 | 4 | 8 | 12 | 16 | 16 | 16
Actual | 0 | 5 | 5 | 8 | 11 | 14 | 16 | [13 empty] | 147
Revised Plan | 15 | 15 | 15 | 32 | 51 | 51 | 70 | 70 | 70 | 70 | 70 | 89 | [8 empty] | 160

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General