## Review Completed
USA:
PAPER SIGN
Task | Initial Test cases Count | Optimized Test case Count | Owner/Reviewer | Start Date | End Date | Status
Standard Product/Embedded/Car Audio/Standard Mobile
Write the test case | 504 | 303 | Puneet | 2018-12-28 | 29-Dec | Review completed
Initial Review |  | 303 | Kamal | 2-Jan | 2-Jan
Final Test cases |  | 164 | Vidusha | 3-Jan | 3-Jan
Pegshelf
Write the test case | 102 | 20 | Puneet | 2018-12-20 | 2018-12-20 | Review completed
Initial Review |  | 22 | Kamal | 2018-12-21 | 2018-12-21
Final Test cases |  | 21 | Vidusha | 2018-12-22 | 2018-12-28
Music and Movies
Write the test case | 100 | 20 | Naveena | 2018-12-20 | 2018-12-20 | Review completed
Initial Review |  | 17 | Puneet | 2018-12-21 | 2018-12-21
Final Test cases |  | 31 | Vidusha | 28-Dec | 28-Dec
Extended Option
Write the test case | 110 | 13 | Puneet | 2018-01-04 | 5-Jan | Review completed
Initial Review |  | 20 | Kamal | 8-Jan | 8-Jan
Final Test cases |  | 20 | Vidusha | 10-Jan | 10-Jan
Mass Display
Write the test case | 100 | 20 | Kamal | 2018-10-18 | 2018-10-20 | Review completed
Final Test cases |  | 21 | Vidusha | 2018-12-12 | 2018-12-19
Magnolia Tag B
Write the test case | 58 | 18 | Chanikya | 2018-12-17 | 2018-12-17 | Review completed
Initial Review |  | 18 | Puneet | 2018-12-20 | 2018-12-20
Final Test cases |  | 14 | Vidusha | 2018-12-21 | 2018-12-21
Magnolia Tag C
Write the test case | 58 | 5 | Priyanka | 2018-12-17 | 2018-12-17 | Review completed
Initial Review |  | 18 | Puneet | 2018-12-21 | 2018-12-21
Final Test cases |  | 14 | Vidusha | 2018-12-21 | 2018-12-22
Standard Sideliner Bundle
Write the test case | 85 | 17 | Naveena | 2018-02-13 | 2018-02-14 | Review completed
Initial Review |  | 17 | Puneet | 2018-02-16 | 2018-02-16
Final Test cases |  | 20 | Isca | 2018-02-20 | 2018-03-01
Mass Display Bundle
Write the test case | 89 | 17 | Naveena | 2018-02-15 | 2018-02-16 | Review completed
Initial Review |  | 17 | Puneet | 2018-02-16 | 2018-02-16
Final Test cases |  | 20 | Isca | 2018-02-20 | 2018-03-01
Non Priced Package
Write the test case | 36 | 11 | Puneet | 2018-01-09 | 2018-01-09 | Review completed
Initial Review |  | 10 | Kamal | 2018-01-09 | 2018-01-09
Final Test cases |  | 9 | Isca | 2018-02-20 | 2018-03-01
Magnolia Bundle Tag
Write the test case | 37 | 6 | Naveena | 2018-12-26 | 2018-12-26 | Review completed
Initial Review |  | 6 | Puneet | 2018-12-26 | 2018-12-26
Final Test cases |  | 12 | Vidusha | 2018-12-28 | 2018-12-28
Magnolia 8x11 Bundle
Write the test case | 41 | 6 | Priyanka | 2018-12-26 | 2018-12-26 | Review completed
Initial Review |  | 6 | Puneet | 2018-12-28 | 2018-12-28
Final Test cases |  | 12 | Vidusha | 2018-12-28 | 2018-12-28
CD Divider
Write the test case | 12 | 6 | Puneet | 14-Dec | 14-Dec | Review completed
Initial Review |  | 5 | Puneet | 15-Dec | 18-Dec
Final Test cases |  | 5 | Vidusha | 18-Dec | 18-Dec
Pricing Grid/Capacity Grid/Feature Grid
Write the test case | 525 | 150 | Puneet/Naveena | 2018-02-20 | 2018-02-23 | Review completed
Initial Review |  | 150 | Puneet | 23-Feb | 2018-02-23
Final Test cases |  | 151 | Isca | 2018-02-27 | 2018-03-05
USA:
ESL
ESL PEG Shelf and Music & Movie
Write the test case | 47 | 32 | Puneet | 2018-01-10 | 2018-01-11 | Review Completed
Initial Review |  | 32 | Isca | 12-Jan | 12-Jan
Review the test case |  | 32 | Vidusha | 20-Feb | 20-Feb
ESL Mass Display
Write the test case | 42 | 23 | Puneet | 2018-01-09 | 2018-01-10 | Review Completed
Initial Review |  | 23 | Isca | 12-Jan | 12-Jan
Review the test case |  | 23 | Isca | 20-Feb | 20-Feb
ESL Standard Product/Embedded/Car Audio/Standard Mobile
Write the test case | 268 | 169 | Kamal/Puneet | 2018-01-11 | 2018-01-15 | Review Completed
Final Test cases |  | 178 | Isca | 2018-02-19 | 2018-03-01
ESL Pricing Grid/Capacity Grid/Feature Grid
Write the test case | 225 | 144 | Puneet/Naveena | 2018-02-20 | 2018-02-26 | Review Completed
Final Test cases |  | 144 | Isca | 2018-03-02 | 2018-03-02
ESL Open Box
Write the test case | 7 | 10 | Isca | 2018-03-05 | 2018-03-05 | Review Completed
Review the test case |  | 4 | Vidusha | 2018-03-06 | 2018-03-06
USA:
Feeds
OMT - GC, Pricing, PKG Pricing, ESL Pricing | - | 198 | Puneet/Priyanka | 2018-01-16 | 2018-03-08 | Test Cases write completed
RMS - SKU, SKU_CHAIN, DCS, INV, UPC, ESLINV | - | 18 | Priyanka/Darshan | 2018-02-22 | 2018-02-22 | Test Cases write completed
Magellan Feeds(SKU_SPEC,SKU_CON,SKU_REVIEW, SKU2) | - | 18 | Priyanka/Darshan | 2018-02-23 | 2018-02-26 | Test Cases write completed
PLNGRM,BADGE,SKU_DOWNSTOCK,STOR,LIC_PLATE, GSP | - | 27 | Priyanka/Darshan | 2018-03-08 | 2018-03-08 | Test Cases write completed
Review the test case | - | - | Vidusha/Isca | 2018-03-08 | 2018-03-12 | Review Completed
MEXICO:
PAPER SIGN
Task | Initial Test cases Count | Optimized Test case Count | Owner/Reviewer | Start Date | End Date | Status
Standard Product
Write the test case | 59 | 19 | Kamal | 2018-03-05 | 2018-03-06 | Review Completed
Initial Review |  | 19 | Naveena | 2018-03-09 | 2018-03-09
Final Test cases |  | 18 | Isca | 2018-03-13 | 13-Mar
Pegshelf
Write the test case | 50 | 16 | Naveena | 2018-03-05 | 2018-03-06 | Review Completed
Initial Review |  | 12 | Kamal | 2018-03-12 | 2018-03-12
Final Test cases |  | 10 | Isca | 2018-03-13 | 2018-03-13
Standard Sideliner Bundle
Write the test case | 60 | 13 | Naveena | 2018-03-07 | 2018-03-08 | Review Completed
Initial Review |  | 11 | Kamal | 2018-03-12 | 2018-03-12
Final Test cases |  | 11 | Isca | 14-Mar | 14-Mar
Non Priced Package
Write the test case | 28 | 6 | Darshan | 2018-03-09 | 2018-03-09 | Review Completed
Initial Review |  | 6 | Priyanka | 2018-03-12 | 2018-03-12
Final Test cases |  | 6 | Isca | 14-Mar | 14-Mar
Music and Movies
Write the test case | 30 | 6 | Darshan | 2018-03-06 | 2018-03-06 | Review Completed
Initial Review |  | 6 | Naveena | 2018-03-12 | 2018-03-12
Final Test cases |  | 6 | Isca | 2018-03-15 | 2018-03-15
Extended Option
Write the test case | 44 | 18 | Kamal | 2018-03-07 | 2018-03-08 | Review Completed
Initial Review |  | 13 | Naveena | 12-Mar | 12-Mar
Final Test cases |  | 13 | Isca | 15-Mar | 2018-03-15
CD Divider SKU
Write the test case | 15 | 4 | Darshan | 2018-03-07 | 2018-03-07 | Review Completed
Initial Review |  | 4 | Priyanka | 2018-03-09 | 2018-03-09
Final Test cases |  | 4 | Isca | 16-Mar | 16-Mar
CD Divider
Write the test case | 9 | 9 | Darshan | 2018-03-05 | 2018-03-05 | Review Completed
Initial Review |  | 9 | Priyanka | 2018-03-06 | 2018-03-06
Final Test cases |  | 9 | Isca | 16-Mar | 16-Mar

## USA
Task | Initial Test cases Count | Optimized Test case Count | Owner/Reviewer | Start Date | End Date | Status
Copywriter
CW Home Page | 350 | 1 | Isca | 2018-02-21 | 2018-03-05 | Review Completed
My SKUs |  | 29 | Isca/Priyanka |  |  | Review Completed
Others'SKUs |  | 15 | Priyanka |  |  | Review Completed
My Value Packages |  | 26 | Puneet |  |  | Review Completed
Others'Value Package |  | 12 | Priyanka |  |  | Review Completed
My ES Signs |  | 21 | Darshan |  |  | Review Completed
Others'ES Signs |  | 10 | Priyanka |  |  | Review Completed
My Mobile Skus |  | 12 | Darshan |  |  | Review Completed
Others Mobile Skus |  | 6 | Priyanka |  |  | Review Completed
My Price Grids |  | 33 | Puneet |  |  | Review Completed
Others Price Grids |  | 8 | Naveena |  |  | Review Completed
Maintenance |  | 85 | Naveena |  |  | Review Completed
ESL Preview |  | 8 | Isca |  |  | Review Completed
Published SKUs Report |  | 1 | Naveena |  |  | Review Completed
Review the test case |  | - | Vidusha/Isca/Puneet | 2018-03-12 | 2018-03-12 | Review Completed

## MEXICO
PAPER SIGN
Task | Initial Test cases Count | Optimized Test case Count | Owner/Reviewer | Start Date | End Date | Status
Feeds
Write the test case | 207 | 48 | Kamal/Darshan | 2018-03-13 | 2018-03-20 | Completed
Final Test cases |  | 48 | Isca | 22-Mar | 2018-03-23 | Completed
Copywriter
Write the test case | 245 | 155 | Naveena/Priyanka | 2018-03-13 | 2018-03-16 | Completed
Final Test cases |  | 151 | Isca | 19-Mar | 2018-03-22 | Completed
Task | Initial Test cases Count | Optimized Test case Count | Owner/Reviewer | Start Date | End Date | Status
Copywriter
CW Home Page | 245 | 1 | Naveena | 2018-03-13 | 2018-03-16 | Test Case Write Completed
My SKUs |  | 28 | Priyanka |  |  | Test Case Write Completed
Others'SKUs |  | 14 | Priyanka |  |  | Test Case Write Completed
My Value Packages |  | 23 | Naveena |  |  | Test Case Write Completed
Others'Value Package |  | 9 | Naveena |  |  | Test Case Write Completed
My ES Signs |  | 21 | Priyanka |  |  | Test Case Write Completed
Others'ES Signs |  | 10 | Priyanka |  |  | Test Case Write Completed
Maintenance |  | 48 | Naveena |  |  | Test Case Write Completed
Published SKUs report |  | 1 | Naveena |  |  | Test Case Write Completed
Review the test case |  | 151 | Kamal/Naveena | 19-Mar | 2018-03-22 | Completed

## Sheet2
Areas | Regression | Optimized Regression | Comments
Paper Standard version | 504 | 164 | 1.There are 5 version of Standard Template,3 version of Pricing Grid, & 2 Version of Peg Label. 2.4 layers are common in all version.So that executing only one time. 3.English,Spanish,New York scenarios are merged with one single testcases for each requirement. 4.Pricing variations related scenarios are merged with one single testcases for each requirement. 5.CW print preview and Store print preview scenarios have been combined. 6.Sign Audit scenarios are merged with functional scenarios. 7.Feed related scenarios have been separated in feed validation. 8.2 layers are commomn in Capacity grid,Activation grid,feature grid.so that related scenarios are removed from two tempalte and executing only one time. 9.Spanish and CPE is no longer available for Pricing grid.So that removed related scenarios. 10.Barcode & Customer reviews scenarios are out of scope for few templates. 11.Negative validation testcases have been included with valid input testcases.
Peg Label | 102 | 21
Music & Movie | 100 | 31
Extended Option | 110 | 20
Mass Display | 100 | 21
Magnolia Tag B | 58 | 14
Magnolia Tag C | 58 | 14
Magnolia small Bundle | 37 | 12
Magnolia Large Bundle | 41 | 12
CD Divider | 12 | 5
ESL PegLabel | 47 | 32
ESL Mass Display | 42 | 23
Small Bundle | 85 | 20
Large Bundle | 89 | 20
Non Priced Bundle | 36 | 9
Paper Pricing Grid | 525 | 180
ESL Pricing Grid | 225 | 144
ESL Standard All version | 268 | 178
ESL Open Box | 7 | 4 | This is newly introduced in ESL.
Copywriter | 250 | 249 | Started Test Cases drafting to follow the Automation approach.
Store UI | 319 | 66 | Test Cases have written to follow the Automation Approach
Mobile UI | 162 | 64 | Test Cases have written to follow the Automation approach
ESL UI | 110 | 101 | Test Cases have written to follow the Automation approach
Grand Total | 3322 | 1404

## Sheet4
Component | Initial Count | Total Test Cases | % Completion | Status | Start Date | End Date
ESL UI | 110 | 101 | 100 | Completed
Mobile UI | 162 | 64 | 100 | Completed
Store UI | 319 | 66 | 100 | Completed
Paper Templates | 1857 | 543 | 100 | Completed | 2017-01-10 | 2018-03-07
ESL Templates | 589 | 381 | 100 | Completed | 2018-01-01 | 2018-03-07
Feeds | No Initial Scenarios | 261 | 100 | Completed | 2018-01-01 | 2018-03-09
Copywriter | 350 | 268 | 100 | Completed | 2018-02-21 | 2018-03-12
Total Scenarios | 3387 | 1684 | 100
Mexico
Component | Initial Count | Total Test Cases | % Completion | Status | Start Date | End Date
Paper Templates | 295 | 77 | 100 | Completed | 2018-03-05 | 2018-03-16
Feeds | 207 | 48 | 100 | Completed | 2018-03-13 | 2018-03-23
Copywriter | 245 | 151 | 100 | Completed | 2018-03-13 | 2018-03-22

## Sheet1
Test Suite | Total Scripts | Executed | Passed | Failed | In Progress | No Run | Blocked | Deferred | Pass % | Execution %
[9 empty] | (Per Executed) |  |  | ESL STD | pass | blocked | No Run
Mass Display | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 100% | 100% |  | ESL Embedded | 20 | 3 | 0 | Side banner
Music &Movie | 31 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 100% | 100% |  | Car Audio | 7 | 0 | 0
Peg Label | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 100% | 100% |  | Standard Mobile | 107 | 0 | 0
Magnolia Tag B | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 100% | 100% |  | Standard Product | 25 | 0 | 0
Magnolia Tag C | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 100% | 100% |  | Unlocked | 8 | 0 | 5 | GC
Standard Product | 164 | 163 | 163 | 0 | 0 | 1 | 0 | 0 | 100% | 99.39% |  |  | 167 | 3 | 5
Pricing Grid | 151 | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Magnolia Small Bundle | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Magnolia Large Bundle | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
CD Divider | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Bundle & Save | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Bundle & Save Large | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Extended Option | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Non Price Bundle | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
ESL_Peg Label & Music and Movie | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
ESL_Standard Product | 167 | 162 | 162 | 0 | 0 | 0 | 5 | 0 | 100% | 97.01%
ESL_Mass Display | 23 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Area | Defect ID | Failed | Blocked
ESL_Grid | 144 | 142 | 139 | 3 | 0 | 0 | 2 | 0 | 97.89% | 98.61% | ESL_Grid | 67135¦67138 | 3 | 2
Copywriter | 268 | 268 | 267 | 1 | 0 | 0 | 0 | 0 | 99.63% | 100% | Copywriter | 67566 | 1
ESL UI Manual | 51 | 41 | 41 | 0 | 0 | 10 | 0 | 0 | 100% | 80.39% | ESL Standard | 67562¦67571 |  | 5
Sign Feeds | 71 | 65 | 65 | 0 | 0 | 0 | 6 | 0 | 100% | 91.55% | Sign Feeds | 67571 |  | 6
ESL UI Automation | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Total |  | 4 | 13
Mobile UI | 64 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Store UI | 46 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Grand Total | 1435 | 1411 | 1407 | 4 | 0 | 11 | 13 | 0 | 99.72% | 98.33%
Test Suite | Total Scripts | Executed | Passed | Failed | In Progress | No Run | Blocked | Deferred | Pass % | Execution %
(Per Executed)
CD Divider Label | 9 | 8 | 8 | 0 | 0 | 0 | 0 | 1 | 100% | 88.89%
CD Divider SKU Sign | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Bundle & Save | 11 | 8 | 8 | 0 | 0 | 0 | 0 | 3 | 100% | 72.73%
Extended Option | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Non Price Bundle | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Peg Label | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Copywriter | 129 | 125 | 124 | 1 | 0 | 0 | 4 | 0 | 99.2% | 96.9%
Music & Movie Label | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Standard Product | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Grand Total | 206 | 198 | 197 | 1 | 0 | 0 | 4 | 4 | 99.49% | 96.12%

## Sheet3
ID | Title | State | Priority | Severity | Assigned To | Changed Date | Closed By | Resolved Date
67562 | Oracle Upgrade_ ESL-Standard product_side banner and top banner | New | 3 | 3 - Medium | Cordero, Francisa-CW | 2018-05-10 13:48
67135 | ESL-Capacity Grid-Unactivated Capacity Grid with 3 Capacity->Unactivated Header is displayed in place of Capacity Header(ex-32,64,128 GB) | New | 2 | 3 - Medium | Vidhusha, Vidhusha - CW | 2018-05-03 01:17
67138 | ESL-Capacity Grid-Unactivated Row is not displayed when 3 Capacity,Unactivated and Unlock SKU is configured. | New | 2 | 3 - Medium | Vidhusha, Vidhusha - CW | 2018-05-03 01:17

## Sheet6
Test Suite | Total Scripts | Executed | Passed | Failed | In Progress | No Run | Blocked | Deferred | Pass % | Execution %
(Per Executed)
Card Member | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Services | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 100% | 100%
Bundle & Save | 29 | 22 | 22 | 0 | 0 | 6 | 1 | 0 | 100% | 75.86%
Grand Total | 54 | 47 | 47 | 0 | 0 | 6 | 1 | 0 | 100% | 87.04%

## Pass2
Test Suite | Total Scripts | Executed | Passed | Failed | In Progress | No Run | Blocked | Deferred | Pass % | Execution % | Automation Status
(Per Executed)
Card Member | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Planning to write scripts
Services | 13 | 10 | 10 | 0 | 0 | 3 | 0 | 0 | 100% | 76.92% | 10 scenarios automated
Bundle & Save | 29 | 25 | 0 | 0 | 0 | 4 | 0 | 0 | 0% | 86.21% | 15 scenarios automated
Grand Total | 54 | 47 | 22 | 0 | 0 | 7 | 0 | 0 | 46.81% | 87.04%

## Sheet7
Test Suite | Total Scripts | Executed | Passed | Failed | In Progress | No Run | Blocked | Deferred | Pass % | Execution % | Automation Status
(Per Executed)
Product Details | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Automated
Other Options | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Automated
Open Box | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Automated
Related Products | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | #DIV/0! | 0% | Automated
Activation Offers | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | Automated
Map | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | #DIV/0! | 0% | Not Automated
Grand Total | 39 | 28 | 28 | 0 | 0 | 11 | 0 | 0 | 100% | 71.79%