## Summary
Functional Area | Total Scripts | Scripts Executed | Passed | Failed | No Run | In-Progress | Blocked | Deferred | % Passed per Executed | % Passed per Total | % Executed
Non Priced | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Bundle and Save | 64 | 60 | 59 | 1 | 4 | 0 | 0 | 0 | 98.33% | 92.19% | 93.75%
Large Bundle and save | 59 | 58 | 57 | 1 | 1 | 0 | 0 | 0 | 98.28% | 96.61% | 98.31%
Mass Display | 64 | 63 | 63 | 0 | 1 | 0 | 0 | 0 | 100% | 98.44% | 98.44%
Pricing Grid | 57 | 39 | 33 | 6 | 11 | 0 | 7 | 0 | 84.62% | 57.89% | 68.42%
Music and Movies | 53 | 51 | 51 | 0 | 2 | 0 | 0 | 0 | 100% | 96.23% | 96.23%
Peg Hook label | 68 | 66 | 66 | 0 | 2 | 0 | 0 | 0 | 100% | 97.06% | 97.06%
Standard Product Template | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Store UI New changes | 9 | 6 | 5 | 1 | 2 | 0 | 1 | 0
Copywriter New Changes | 108 | 79 | 66 | 13 | 18 | 0 | 11 | 0 | 83.54% | 61.11% | 73.15%
Total | 482 | 422 | 400 | 22 | 41 | 0 | 19 | 0 | 94.79% | 82.99% | 87.55%

## USTDPRD3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Standard Product Template
2 | Standard Product Template
3 | Standard Product Template
4 | Standard Product Template
5 | Standard Product Template
6 | Standard Product Template
7 | Standard Product Template
8 | Standard Product Template
9 | Standard Product Template
10 | Standard Product Template
11 | Standard Product Template
12 | Standard Product Template
13 | Standard Product Template
14 | Standard Product Template
15 | Standard Product Template
16 | Standard Product Template
17 | Standard Product Template
18 | Standard Product Template
19 | Standard Product Template
20 | Standard Product Template
21 | Standard Product Template
22 | Standard Product Template
23 | Standard Product Template
24 | Standard Product Template
25 | Standard Product Template
26 | Standard Product Template
27 | Standard Product Template
28 | Standard Product Template
29 | Standard Product Template
30 | Standard Product Template
31 | Standard Product Template | [6 empty] | Defect ID - Store00031320
32 | Standard Product Template
33 | Standard Product Template
34 | Standard Product Template
35 | Standard Product Template
36 | Standard Product Template
37 | Standard Product Template
38 | Standard Product Template
39 | Standard Product Template
40 | Standard Product Template
41 | Standard Product Template
42 | Standard Product Template
43 | Standard Product Template
44 | Standard Product Template
45 | Standard Product Template
46 | Standard Product Template
47 | Standard Product Template
48 | Standard Product Template
49 | Standard Product Template
50 | Standard Product Template
51 | Standard Product Template
52 | Standard Product Template
53 | Standard Product Template
54 | Standard Product Template
55 | Standard Product Template
56 | Standard Product Template
57 | Standard Product Template
58 | Standard Product Template
59 | Standard Product Template
60 | Standard Product Template
61 | Standard Product Template
62 | Standard Product Template
63 | Standard Product Template
64 | Standard Product Template
65 | Standard Product Template
66 | Standard Product Template
67 | Standard Product Template
68 | Standard Product Template
69 | Standard Product Template
70 | Standard Product Template
71 | Standard Product Template
72 | Standard Product Template
73 | Standard Product Template
74 | Standard Product Template
75 | Standard Product Template
76 | Standard Product Template
77 | Standard Product Template
|  | Total | 0
|  | Pass | 0
|  | Fail | 0
|  | NoRun | 0
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## UMASS3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Mass Display | MD0.1 | Kamal | 2015-08-10 | Pass
2 | Mass Display | MD1.1 | Kamal | 2015-08-10 | Pass
3 | Mass Display | MD1.2 | Kamal | 2015-08-10 | Pass
4 | Mass Display | MD1.3 | Kamal | 2015-08-10 | Pass
5 | Mass Display | MD1.4 | Kamal | 2015-08-10 | Pass
6 | Mass Display | MD1.5 | Kamal | 2015-08-10 | Pass
7 | Mass Display | MD1.6 | Kamal | 2015-08-10 | Pass
8 | Mass Display | MD1.7 | Kamal | 2015-08-10 | Pass
9 | Mass Display | MD2.1 | Kamal | 2015-08-10 | Pass
10 | Mass Display | MD2.2 | Kamal | 2015-08-10 | Pass
11 | Mass Display | MD2.3 | Kamal | 2015-08-10 | Pass
12 | Mass Display | MD2.4 | Kamal | 2015-08-10 | Pass
13 | Mass Display | MD3.1 | Kamal | 2015-08-10 | Pass
14 | Mass Display | MD4.1 | Kamal | 2015-08-10 | Pass
15 | Mass Display | MD4.2 | Kamal | 2015-08-10 | Pass
16 | Mass Display | MD4.3 | Kamal | 2015-08-10 | Pass
17 | Mass Display | MD4.4 | Kamal | 2015-08-10 | Pass
18 | Mass Display | MD4.5 | Kamal | 2015-08-10 | Pass
19 | Mass Display | MD4.6 | Kamal | 2015-08-10 | Pass
20 | Mass Display | MD4.7 | Kamal | 2015-08-10 | Pass
21 | Mass Display | MD4.8 | Kamal | 2015-08-10 | Pass
22 | Mass Display | MD4.9 | Kamal | 2015-08-10 | Pass
23 | Mass Display | MD4.10 | Kamal | 2015-08-10 | Pass
24 | Mass Display | MD4.11 | Kamal | 2015-08-10 | Pass
25 | Mass Display | MD4.12 | Kamal | 2015-08-10 | Pass
26 | Mass Display | MD4.13 | Kamal | 2015-08-10 | Pass
27 | Mass Display | MD4.14 | Kamal | 2015-08-10 | Pass
28 | Mass Display | MD5.1 | Puneet | 2015-08-11 | Pass
29 | Mass Display | MD5.2 |  |  | N/A
30 | Mass Display | MD5.3 | Kamal | 2015-08-11 | Pass
31 | Mass Display | MD5.4 | Kamal | 2015-08-11 | Pass
32 | Mass Display | MD5.5 | Kamal | 2015-08-11 | Pass
33 | Mass Display | MD5.6 | Kamal | 2015-08-13 | Pass |  |  | Defect has been fixed |  | CCM Defect_ID :37481
34 | Mass Display | MD6.1 | Kamal | 2015-08-10 | Pass
35 | Mass Display | MD7.1 | Kamal | 2015-08-10 | Pass
36 | Mass Display | MD8.1 | Kamal | 2015-08-10 | Pass
37 | Mass Display | MD9.1 | Kamal | 2015-08-11 | Pass
38 | Mass Display | MD9.2 | Kamal | 2015-08-10 | Pass
39 | Mass Display | MD9.3 | Kamal | 2015-08-11 | Pass
40 | Mass Display | MD10.1 | Puneet | 2015-08-11 | Pass
41 | Mass Display | MD10.2 | Puneet | 2015-08-11 | Pass
42 | Mass Display | MD11.1 | Kamal | 2015-08-10 | Pass
43 | Mass Display | MD11.2 | Kamal | 2015-08-10 | Pass
44 | Mass Display | MD12.1 | Kamal | 2015-08-10 | Pass
45 | Mass Display | MD12.2 | Kamal | 2015-08-11 | Pass
46 | Mass Display | MD12.3 | Kamal | 2015-08-10 | Pass
47 | Mass Display | MD12.4 | Kamal | 2015-08-11 | Pass
48 | Mass Display | MD12.5 | Kamal | 2015-08-10 | Pass
49 | Mass Display | MD13.1 | Kamal | 2015-08-12 | Pass
50 | Mass Display | MD13.2 | Kamal | 2015-08-11 | Pass
51 | Mass Display | MD14.1 | Puneet | 2015-08-11 | Pass
52 | Mass Display | MD14.2 | Puneet | 2015-08-11 | Pass
53 | Mass Display | MD14.3 | Puneet | 2015-08-11 | Pass
54 | Mass Display | MD14.4 | Kamal | 2015-08-13 | Pass
55 | Mass Display | MD15.1 |  |  | No Run
56 | Mass Display | MD15.2 | Kamal | 2015-08-10 | Pass
57 | Mass Display | MD15.3 | Kamal | 2015-08-11 | Pass
58 | Mass Display | MD15.4 | Kamal | 2015-08-10 | Pass
59 | Mass Display | MD15.5 | Kamal | 2015-08-11 | Pass
60 | Mass Display | MD15.6 | Puneet | 2015-08-14 | Pass
61 | Mass Display | MD15.7 | Puneet | 2015-08-14 | Pass
62 | Mass Display | MD15.8 | Puneet | 2015-08-14 | Pass
63 | Mass Display | MD15.9 | Puneet | 2015-08-14 | Pass
64 | Mass Display | MD15.10 | Puneet | 2015-08-14 | Pass
65 | Mass Display | MD15.11 | Puneet | 2015-08-14 | Pass
|  | Total | 64
|  | Pass | 63
|  | Fail | 0
|  | NoRun | 1
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## Pricing Grid
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Pricing Grid Template | PG1.1 | Puneet | 2015-08-25 | Pass
2 | Pricing Grid Template | PG1.2 | Puneet | 2015-08-25 | Pass
3 | Pricing Grid Template | PG1.3 |  |  | No Run
4 | Pricing Grid Template | PG1.4 |  |  | No Run
5 | Pricing Grid Template | PG2.1 | Puneet | 2015-08-25 | Pass
6 | Pricing Grid Template | PG3.1 | Puneet | 2015-08-25 | Fail |  |  | Defect_id=CCM37922
7 | Pricing Grid Template | PG3.2 |  |  | Blocked |  |  | Defect_id=CCM37922
8 | Pricing Grid Template | PG3.3 |  |  | Blocked |  |  | Defect_id=CCM37922
9 | Pricing Grid Template | PG4.1 |  |  | Blocked |  |  | Defect_id=CCM37922
10 | Pricing Grid Template | PG4.2 |  |  | Blocked |  |  | Defect_id=CCM37922
11 | Pricing Grid Template | PG4.3 |  |  | Blocked |  |  | Defect_id=CCM37922
12 | Pricing Grid Template | PG5.1 | Puneet | 2015-08-25 | Pass
13 | Pricing Grid Template | PG6.1 | Puneet | 2015-08-25 | Pass
14 | Pricing Grid Template | PG6.2 | Puneet | 2015-08-25 | Pass
15 | Pricing Grid Template | PG6.3 | Puneet | 2015-08-25 | Pass
16 | Pricing Grid Template | PG7.1 | Puneet | 2015-08-25 | Pass
17 | Pricing Grid Template | PG8.1 |  |  | No Run
18 | Pricing Grid Template | PG9.1 | Puneet | 2015-08-25 | Pass
19 | Pricing Grid Template | PG10.1 | Puneet | 2015-08-25 | Pass
20 | Pricing Grid Template | PG11.1 | Puneet | 2015-08-25 | Fail |  |  | Defect_id=CCM38284
21 | Pricing Grid Template | PG12.1 |  |  | N/A |  |  | As discussed with DEV,Expiry date will not be displayed as it is out of scope.
22 | Pricing Grid Template | PG12.2 |  |  | N/A |  |  | As discussed with DEV,Expiry date will not be displayed as it is out of scope.
23 | Pricing Grid Template | PG12.3 |  |  | N/A |  |  | As discussed with DEV,Expiry date will not be displayed as it is out of scope.
24 | Pricing Grid Template | PG13.1 | Puneet | 2015-08-25 | Pass
25 | Pricing Grid Template | PG14.1 | Priyabrat | 2015-08-26 | Pass
26 | Pricing Grid Template | PG14.2 | Priyabrat | 2015-08-26 | Pass
27 | Pricing Grid Template | PG14.3 | Priyabrat | 2015-08-26 | Pass
28 | Pricing Grid Template | PG15.1 |  |  | No Run
29 | Pricing Grid Template | PG15.2 |  |  | No Run
30 | Pricing Grid Template | PG16.1 | Priyabrat | 2015-08-26 | Fail | 2015-08-26 |  |  | CCM 38352
31 | Pricing Grid Template | PG16.2 | Priyabrat | 2015-08-26 | Fail |  |  |  | CCM38354
32 | Pricing Grid Template | PG16.3 | Priyabrat | 2015-08-26 | Pass
33 | Pricing Grid Template | PG17.1 | Priyabrat | 2015-08-26 | Fail |  |  |  | CCM38360
34 | Pricing Grid Template | PG17.2 | Priyabrat | 2015-08-26 | Fail |  |  |  | CCM38360
35 | Pricing Grid Template | PG17.3 |  |  | Blocked |  |  |  | CCM38360
36 | Pricing Grid Template | PG18.1 |  |  | Blocked |  |  |  | CCM38360
37 | Pricing Grid Template | PG19.1 | Priyabrat | 2015-08-26 | Pass
38 | Pricing Grid Template | PG20.1 |  |  | No Run
39 | Pricing Grid Template | PG21.1 | Puneet | 2015-08-26 | Pass
40 | Pricing Grid Template | PG21.2 | Puneet | 2015-08-26 | Pass
41 | Pricing Grid Template | PG21.3 | Puneet | 2015-08-26 | Pass
42 | Pricing Grid Template | PG21.4 | Puneet | 2015-08-26 | Pass
43 | Pricing Grid Template | PG21.5 | Puneet | 2015-08-26 | Pass
44 | Pricing Grid Template | PG21.6 | Puneet | 2015-08-26 | Pass
45 | Pricing Grid Template | PG22.1 |  |  | No Run
46 | Pricing Grid Template | PG22.2 |  |  | No Run
47 | Pricing Grid Template | PG22.3 |  |  | No Run
48 | Pricing Grid Template | PG22.4 | Puneet | 2015-08-28 | Pass
49 | Pricing Grid Template | PG22.5 | Puneet | 2015-08-28 | Pass
50 | Pricing Grid Template | PG22.6 | Puneet | 2015-08-28 | Pass
51 | Pricing Grid Template | PG23.1 |  |  | No Run
52 | Pricing Grid Template | PG23.2 |  |  | No Run
53 | Pricing Grid Template | PG23.3 | Puneet | 2015-08-27 | Pass
54 | Pricing Grid Template | PG23.4 | Puneet | 2015-08-27 | Pass
55 | Pricing Grid Template | PG23.5 | Puneet | 2015-08-27 | Pass
56 | Pricing Grid Template | PG23.6 | Puneet | 2015-08-27 | Pass
57 | Pricing Grid Template | PG24.1 | Puneet | 2015-08-28 | Pass
58 | Pricing Grid Template | PG24.2 | Puneet | 2015-08-28 | Pass
59 | Pricing Grid Template | PG24.3 | Puneet | 2015-08-28 | Pass
60 | Pricing Grid Template | PG24.4 | Puneet | 2015-08-28 | Pass
|  | Total | 57
|  | Pass | 33
|  | Fail | 6
|  | NoRun | 11
|  | Blocked | 7
|  | In Progress | 0
|  | Deferred | 0

## UPEGSHF3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Peg Hook label | PH1.1 | Priyabrat | 2015-08-10 | Pass
2 | Peg Hook label | PH1.2 | Priyabrat | 2015-08-10 | Pass
3 | Peg Hook label | PH1.3 | Priyabrat | 2015-08-10 | Pass
4 | Peg Hook label | PH1.4 | Priyabrat | 2015-08-10 | Pass
5 | Peg Hook label | PH2.1 | Priyabrat | 2015-08-10 | Pass
6 | Peg Hook label | PH2.2 | Priyabrat | 2015-08-10 | Pass
7 | Peg Hook label | PH2.3 | Priyabrat | 2015-08-10 | Pass
8 | Peg Hook label | PH2.4 | Priyabrat | 2015-08-10 | Pass
9 | Peg Hook label | PH2.5 | Priyabrat | 2015-08-10 | Pass
10 | Peg Hook label | PH2.6 | Priyabrat | 2015-08-10 | Pass
11 | Peg Hook label | PH2.7 | Priyabrat | 2015-08-10 | Pass
12 | Peg Hook label | PH2.8 | Priyabrat | 2015-08-10 | Pass
13 | Peg Hook label | PH2.9 | Priyabrat | 2015-08-10 | Pass
14 | Peg Hook label | PH2.10 | Priyabrat | 2015-08-10 | Pass
15 | Peg Hook label | PH2.11 | Priyabrat | 2015-08-10 | Pass
16 | Peg Hook label | PH2.12 | Priyabrat | 2015-08-10 | Pass
17 | Peg Hook label | PH3.1 | Priyabrat | 2015-08-10 | Pass
18 | Peg Hook label | PH3.2 | Priyabrat | 2015-08-10 | Pass
19 | Peg Hook label | PH3.3 | Priyabrat | 2015-08-10 | Pass
20 | Peg Hook label | PH3.4 | Priyabrat | 2015-08-10 | Pass
21 | Peg Hook label | PH4.1 | Priyabrat | 2015-08-10 | Pass
22 | Peg Hook label | PH4.2 | Priyabrat | 2015-08-11 | Pass
23 | Peg Hook label | PH4.3 |  |  | N/A |  |  | As dicussed with Dev team Manufacturere info will be fetched from CW only not from sku2 and sku table.So this test case is not in scope.
24 | Peg Hook label | PH4.4 | Priyabrat | 2015-08-11 | N/A |  |  | As dicussed with Dev team Manufacturere info will be fetched from CW only not from sku2 and sku table.So this test case is not in scope. |  | 37352
25 | Peg Hook label | PH5.1 | Priyabrat | 2015-08-10 | Pass
26 | Peg Hook label | PH5.2 | Priyabrat | 2015-08-10 | Pass
27 | Peg Hook label | PH5.3 | Priyabrat | 2015-08-10 | Pass
28 | Peg Hook label | PH5.4 | Priyabrat | 2015-08-10 | Pass
29 | Peg Hook label | PH5.5 | Priyabrat | 2015-08-10 | Pass
30 | Peg Hook label | PH6.1 | Priyabrat | 2015-08-11 | Pass
31 | Peg Hook label | PH6.2 | Priyabrat | 2015-08-11 | Pass
32 | Peg Hook label | PH6.3 | Priyabrat | 2015-08-11 | Pass
33 | Peg Hook label | PH6.4 | Priyabrat | 2015-08-11 | Pass
34 | Peg Hook label | PH7.1 | Priyabrat | 2015-08-11 | Pass
35 | Peg Hook label | PH8.1 | Priyabrat | 2015-08-11 | Pass
36 | Peg Hook label | PH8.2 | Priyabrat | 2015-08-11 | Pass
37 | Peg Hook label | PH8.3 | Priyabrat | 2015-08-11 | Pass
38 | Peg Hook label | PH8.4 | Priyabrat | 2015-08-11 | Pass
39 | Peg Hook label | PH8.5 | Priyabrat | 2015-08-11 | Pass
40 | Peg Hook label | PH8.6 | Priyabrat | 2015-08-11 | Pass
41 | Peg Hook label | PH9.1 | Priyabrat | 2015-08-11 | Pass
42 | Peg Hook label | PH10.1 | Priyabrat | 2015-08-11 | Pass
43 | Peg Hook label | PH10.2 | Priyabrat | 2015-08-11 | Pass
44 | Peg Hook label | PH11.1 | Priyabrat | 2015-08-11 | Pass
45 | Peg Hook label | PH12.1 | Priyabrat | 2015-08-11 | Pass
46 | Peg Hook label | PH13.1 | Priyabrat | 2015-08-11 | Pass
47 | Peg Hook label | PH13.2 | Priyabrat | 2015-08-11 | Pass
48 | Peg Hook label | PH13.3 | Priyabrat | 2015-08-11 | Pass
49 | Peg Hook label | PH14.1 | Priyabrat | 2015-08-11 | Pass
50 | Peg Hook label | PH14.2 | Priyabrat | 2015-08-11 | Pass
51 | Peg Hook label | PH15.1 | Priyabrat | 2015-08-11 | Pass
52 | Peg Hook label | PH15.2 | Priyabrat | 2015-08-11 | Pass
53 | Peg Hook label | PH16.1 | Priyabrat | 2015-08-11 | Pass
54 | Peg Hook label | PH16.2 | Priyabrat | 2015-08-11 | Pass
55 | Peg Hook label | PH16.3 | Priyabrat | 2015-08-11 | Pass
56 | Peg Hook label | PH16.4 | Priyabrat | 2015-08-11 | Pass
57 | Peg Hook label | PH 17.1 | Priyabrat | 2015-08-11 | Pass
58 | Peg Hook label | PH18.1 |  |  | No Run
59 | Peg Hook label | PH18.2 | Puneet | 2015-08-12 | Pass
60 | Peg Hook label | PH18.3 | Puneet | 2015-08-12 | Pass
61 | Peg Hook label | PH18.4 | Puneet | 2015-08-12 | Pass
62 | Peg Hook label | PH18.5 | Puneet | 2015-08-12 | Pass
63 | Peg Hook label | PH18.6 | Puneet | 2015-08-12 | Pass
64 | Peg Hook label | PH18.7 | Puneet | 2015-08-12 | Pass
65 | Peg Hook label | PH18.8 | Puneet | 2015-08-12 | Pass
66 | Peg Hook label | PH18.9 | Puneet | 2015-08-14 | Pass
67 | Peg Hook label | PH18.10 |  |  | No Run
68 | Peg Hook label | PH18.11 | Puneet | 2015-08-14 | Pass
69 | Peg Hook label | PH18.12 | Puneet | 2015-08-14 | Pass
70 | Peg Hook label | PH18.13 | Puneet | 2015-08-14 | Pass
|  | Total | 68
|  | Pass | 66
|  | Fail | 0
|  | NoRun | 2
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## UMUSMOV3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Music and Movies | MM1.1 | Kamal | 2015-08-12 | Pass
2 | Music and Movies | MM1.2 | Kamal | 2015-08-12 | Pass
3 | Music and Movies | MM2.1 | Kamal | 2015-08-12 | Pass
4 | Music and Movies | MM2.2 | Kamal | 2015-08-12 | Pass
5 | Music and Movies | MM3.1 | Kamal | 2015-08-12 | Pass
6 | Music and Movies | MM3.2 | Kamal | 2015-08-12 | Pass
7 | Music and Movies | MM3.3 | Kamal | 2015-08-12 | Pass
8 | Music and Movies | MM4.1 | Kamal | 2015-08-12 | Pass
9 | Music and Movies | MM4.2 | Kamal | 2015-08-12 | Pass
10 | Music and Movies | MM4.3 | Kamal | 2015-08-12 | Pass
11 | Music and Movies | MM4.4 | Kamal | 2015-08-12 | Pass
12 | Music and Movies | MM4.5 | Kamal | 2015-08-12 | Pass
13 | Music and Movies | MM4.6 | Kamal | 2015-08-12 | Pass
14 | Music and Movies | MM4.7 | Kamal | 2015-08-12 | Pass
15 | Music and Movies | MM4.8 | Kamal | 2015-08-12 | Pass
16 | Music and Movies | MM4.9 | Kamal | 2015-08-12 | Pass
17 | Music and Movies | MM4.10 | Kamal | 2015-08-12 | Pass
18 | Music and Movies | MM4.11 | Kamal | 2015-08-12 | Pass
19 | Music and Movies | MM4.12 | Kamal | 2015-08-12 | Pass
20 | Music and Movies | MM5.1 | Kamal | 2015-08-12 | Pass
21 | Music and Movies | MM6.1 | Kamal | 2015-08-12 | Pass
22 | Music and Movies | MM7.1 | Kamal | 2015-08-12 | Pass
23 | Music and Movies | MM7.2 | Kamal | 2015-08-13 | Pass
24 | Music and Movies | MM8.1 | Kamal | 2015-08-12 | Pass
25 | Music and Movies | MM8.2 | Kamal | 2015-08-13 | Pass
26 | Music and Movies | MM9.1 | Kamal | 2015-08-12 | Pass
27 | Music and Movies | MM9.2 | Kamal | 2015-08-13 | Pass
28 | Music and Movies | MM10.1 | Kamal | 2015-08-13 | Pass
29 | Music and Movies | MM10.2 |  |  | N/A
30 | Music and Movies | MM10.3 | Kamal | 2015-08-13 | Pass
31 | Music and Movies | MM10.4 | Kamal | 2015-08-13 | Pass
32 | Music and Movies | MM10.5 | Kamal | 2015-08-13 | Pass
33 | Music and Movies | MM10.6 | Kamal | 2015-08-13 | Pass |  |  | Defect has been fixed |  | CCM Defect_ID :37481
34 | Music and Movies | MM11.1 | Kamal | 2015-08-12 | Pass
35 | Music and Movies | MM12.1 | Kamal | 2015-08-12 | Pass
36 | Music and Movies | MM12.2 | Kamal | 2015-08-12 | Pass
37 | Music and Movies | MM13.1 | Kamal | 2015-08-12 | Pass
38 | Music and Movies | MM13.2 | Kamal | 2015-08-12 | Pass
39 | Music and Movies | MM14.1 | Kamal | 2015-08-12 | Pass
40 | Music and Movies | MM14.2 | Kamal | 2015-08-12 | Pass
41 | Music and Movies | MM15.1 | Puneet | 2015-08-12 | Pass
42 | Music and Movies | MM15.2 |  |  | No Run
43 | Music and Movies | MM15.3 | Puneet | 2015-08-12 | Pass
44 | Music and Movies | MM15.4 | Puneet | 2015-08-13 | Pass
45 | Music and Movies | MM15.5 | Puneet | 2015-08-12 | Pass
46 | Music and Movies | MM15.6 | Puneet | 2015-08-12 | Pass
47 | Music and Movies | MM15.7 | Puneet | 2015-08-12 | Pass
48 | Music and Movies | MM15.8 |  |  | No Run
49 | Music and Movies | MM15.9 | Puneet | 2015-08-12 | Pass
50 | Music and Movies | MM15.10 | Puneet | 2015-08-14 | Pass
51 | Music and Movies | MM15.11 | Puneet | 2015-08-17 | Pass
52 | Music and Movies | MM15.12 | Puneet | 2015-08-14 | Pass
53 | Music and Movies | MM15.13 | Puneet | 2015-08-14 | Pass
54 | Music and Movies | MM15.14 | Puneet | 2015-08-14 | Pass
|  | Total | 53
|  | Pass | 51
|  | Fail | 0
|  | NoRun | 2
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## UNONPRC3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Non Priced | NP1.1
2 | Non Priced | NP2.1
3 | Non Priced | NP2.2
4 | Non Priced | NP3.1
5 | Non Priced | NP4.1
6 | Non Priced | NP5.1
7 | Non Priced | NP6.1
8 | Non Priced | NP7.1
9 | Non Priced | NP7.2
10 | Non Priced | NP8.1
11 | Non Priced | NP9.1
12 | Non Priced | NP10.1
13 | Non Priced | NP11.1
14 | Non Priced | NP12.1
|  | Total | 0
|  | Pass | 0
|  | Fail | 0
|  | NoRun | 0
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## UBUND3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Bundle and Save | BS1.1 | Priyabrat | 2015-08-12 | Pass
2 | Bundle and Save | BS1.2 | Priyabrat | 2015-08-12 | Pass
3 | Bundle and Save | BS1.3 | Priyabrat | 2015-08-12 | Pass
4 | Bundle and Save | BS2.1 | Priyabrat | 2015-08-12 | Pass
5 | Bundle and Save | BS2.2 | Priyabrat | 2015-08-12 | Pass
6 | Bundle and Save | BS3.1 | Priyabrat | 2015-08-12 | Pass
7 | Bundle and Save | BS4.1 | Priyabrat | 2015-08-12 | Pass
8 | Bundle and Save | BS5.1 | Priyabrat | 2015-08-12 | Pass
9 | Bundle and Save | BS6.1 | Priyabrat | 2015-08-12 | Pass
10 | Bundle and Save | BS6.2 | Kamal | 2015-08-17 | Pass
11 | Bundle and Save | BS7.1 | Priyabrat | 2015-08-12 | Pass
12 | Bundle and Save | BS7.2 | Priyabrat | 2015-08-12 | Pass
13 | Bundle and Save | BS7.3 | Priyabrat | 2015-08-12 | Pass
14 | Bundle and Save | BS8.1 | Priyabrat | 2015-08-12 | Pass
15 | Bundle and Save | BS8.2 | Priyabrat | 2015-08-12 | Pass
16 | Bundle and Save | BS8.3 | Priyabrat | 2015-08-12 | Pass
17 | Bundle and Save | BS9.1 | Priyabrat | 2015-08-12 | Pass
18 | Bundle and Save | BS9.2 | Priyabrat | 2015-08-12 | Pass
19 | Bundle and Save | BS9.3 | Priyabrat | 2015-08-12 | Pass
20 | Bundle and Save | BS10.1 | Priyabrat | 2015-08-12 | Pass
21 | Bundle and Save | BS11.1 | Priyabrat | 2015-08-13 | Pass
22 | Bundle and Save | BS11.2 | Priyabrat | 2015-08-13 | Pass
23 | Bundle and Save | BS12.1 | Priyabrat | 2015-08-13 | Pass
24 | Bundle and Save | BS12.1 | Priyabrat | 2015-08-13 | Pass
25 | Bundle and Save | BS13.1 | Priyabrat | 2015-08-13 | Pass
26 | Bundle and Save | BS14.1 | Priyabrat | 2015-08-13 | Pass
27 | Bundle and Save | BS15.1 | Priyabrat | 2015-08-13 | Pass |  |  | Store00031347
28 | Bundle and Save | BS16.1 | Priyabrat | 2015-08-13 | Pass
29 | Bundle and Save | BS17.1 | Priyabrat | 2015-08-13 | Pass
30 | Bundle and Save | BS17.2 | Priyabrat | 2015-08-13 | Pass
31 | Bundle and Save | BS17.3 | Priyabrat | 2015-08-13 | Pass
32 | Bundle and Save | BS18.1 | Priyabrat | 2015-08-13 | Pass
33 | Bundle and Save | BS18.2 | Priyabrat | 2015-08-13 | Pass |  |  | Store00031351
34 | Bundle and Save | BS20.1 | Priyabrat | 2015-08-13 | Pass |  |  | Store00031351
35 | Bundle and Save | BS21.1 | Priyabrat | 2015-08-13 | Pass
36 | Bundle and Save | BS21.2 | Priyabrat | 2015-08-13 | Pass
37 | Bundle and Save | BS22.1 | Priyabrat | 2015-08-13 | Pass
38 | Bundle and Save | BS22.2 | Priyabrat | 2015-08-13 | Pass
39 | Bundle and Save | BS23.1 | Priyabrat | 2015-08-14 | Pass
40 | Bundle and Save | BS23.2 | Priyabrat | 2015-08-14 | Fail |  |  | CCM37618
41 | Bundle and Save | BS24.1 | Priyabrat | 2015-08-14 | Pass
42 | Bundle and Save | BS25.1 | Priyabrat | 2015-08-14 | Pass
43 | Bundle and Save | BS25.2 | Priyabrat | 2015-08-14 | Pass
44 | Bundle and Save | BS26.1 | Priyabrat | 2015-08-14 | Pass
45 | Bundle and Save | BS27.1 | Priyabrat | 2015-08-14 | Pass
46 | Bundle and Save | BS28.1 | Priyabrat | 2015-08-14 | Pass
47 | Bundle and Save | BS29.1 | Priyabrat | 2015-08-14 | Pass
48 | Bundle and Save | BS30.1 |  |  | No Run
49 | Bundle and Save | BS30.2 | puneet | 2015-08-14 | pass
50 | Bundle and Save | BS30.3 | Puneet | 2015-08-14 | Pass
51 | Bundle and Save | BS30.4 | Puneet | 2015-08-14 | Pass
52 | Bundle and Save | BS30.5 | Puneet | 2015-08-17 | Pass
53 | Bundle and Save | BS30.6 | Puneet | 2015-08-14 | pass
54 | Bundle and Save | BS30.7 | puneet | 2015-08-14 | pass
55 | Bundle and Save | BS30.8 | Puneet | 2015-08-14 | Pass
56 | Bundle and Save | BS30.9 | Puneet | 2015-08-17 | Pass
57 | Bundle and Save | BS30.10 | Puneet | 2015-08-17 | Pass
58 | Bundle and Save | BS30.11 | puneet | 2015-08-17 | Pass
59 | Bundle and Save | BS30.12 | Puneet | 2015-08-17 | Pass
60 | Bundle and Save | BS30.13 | puneet | 2015-08-17 | Pass
60 | Bundle and Save | BS14.1 | Priyabrat | 2015-08-14 | Pass
60 | Bundle and Save | BS14.2 |  |  | No Run
60 | Bundle and Save | BS14.3 |  |  | No Run
60 | Bundle and Save | BS14.4 |  |  | No Run
|  | Total | 64
|  | Pass | 59
|  | Fail | 1
|  | NoRun | 4
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## ULBUND3
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Large Bndle and save | LBS1.1 | Kamal | 2015-08-13 | Pass
2 | Large Bndle and save | LBS2.1 | Kamal | 2015-08-13 | Pass
3 | Large Bndle and save | LBS3.1 | Kamal | 2015-08-13 | Pass
4 | Large Bndle and save | LBS4.1 | Kamal | 2015-08-13 | Pass
5 | Large Bndle and save | LBS4.2 | Kamal | 2015-08-13 | Pass
6 | Large Bndle and save | LBS5.1 | Kamal | 2015-08-13 | Pass
7 | Large Bndle and save | LBS5.2 | Kamal | 2015-08-13 | Pass
8 | Large Bndle and save | LBS5.3 | Kamal | 2015-08-13 | Pass
9 | Large Bndle and save | LBS6.1 | Kamal | 2015-08-13 | Pass
10 | Large Bndle and save | LBS6.2 | Kamal | 2015-08-13 | Pass
11 | Large Bndle and save | LBS6.3 | Kamal | 2015-08-14 | Pass
12 | Large Bndle and save | LBS6.4 | Kamal | 2015-08-13 | Pass
13 | Large Bndle and save | LBS7.1 | Kamal | 2015-08-14 | Pass
14 | Large Bndle and save | LBS7.2 | Kamal | 2015-08-14 | Pass
15 | Large Bndle and save | LBS7.3 | Kamal | 2015-08-13 | Pass
16 | Large Bndle and save | LBS7.4 | Kamal | 2015-08-14 | Pass
17 | Large Bndle and save | LBS8.1 | Kamal | 2015-08-13 | Pass
18 | Large Bndle and save | LBS9.1 | Kamal | 2015-08-17 | Pass
19 | Large Bndle and save | LBS9.2 | Kamal | 2015-08-13 | Pass
20 | Large Bndle and save | LBS10.1 | Kamal | 2015-08-17 | Pass
21 | Large Bndle and save | LBS10.2 | Kamal | 2015-08-14 | Pass
22 | Large Bndle and save | LBS11.1 | Kamal | 2015-08-14 | Pass
23 | Large Bndle and save | LBS12.1 | Puneet | 2015-08-14 | Pass
24 | Large Bndle and save | LBS13.1 | Kamal | 2015-08-14 | Pass
25 | Large Bndle and save | LBS14.1 | Kamal | 2015-08-14 | Pass
26 | Large Bndle and save | LBS15.1 | Kamal | 2015-08-17 | Pass
27 | Large Bndle and save | LBS15.2 | Kamal | 2015-08-17 | Pass
28 | Large Bndle and save | LBS15.3 | Kamal | 2015-08-14 | Pass
29 | Large Bndle and save | LBS16.1 | Kamal | 2015-08-13 | Pass
30 | Large Bndle and save | LBS16.2 | Kamal | 2015-08-14 | Pass
31 | Large Bndle and save | LBS16.3 | Kamal | 2015-08-13 | Pass
32 | Large Bndle and save | LBS17.1 | Puneet | 2015-08-14 | Pass
33 | Large Bndle and save | LBS18.1 | Kamal | 2015-08-14 | Pass
34 | Large Bndle and save | LBS19.1 | Kamal | 2015-08-17 | Pass
35 | Large Bndle and save | LBS19.2 | Kamal | 2015-08-14 | Pass
36 | Large Bndle and save | LBS20.1 | Kamal | 2015-08-17 | Pass
37 | Large Bndle and save | LBS20.2 | Kamal | 2015-08-14 | Pass
38 | Large Bndle and save | LBS21.1 | Kamal | 2015-08-17 | Fail |  |  |  |  | CCM 37618
39 | Large Bndle and save | LBS21.2 | Kamal | 2015-08-14 | Pass
40 | Large Bndle and save | LBS22.1 | Puneet | 2015-08-14 | Pass
41 | Large Bndle and save | LBS23.1 | Kamal | 2015-08-14 | Pass
42 | Large Bndle and save | LBS23.2 | Kamal | 2015-08-13 | Pass
43 | Large Bndle and save | LBS24.1 | Kamal | 2015-08-17 | Pass
44 | Large Bndle and save | LBS24.2 | Kamal | 2015-08-17 | Pass
45 | Large Bndle and save | LBS25.1 | Kamal | 2015-08-17 | Pass
46 | Large Bndle and save | LBS25.2 | Kamal | 2015-08-17 | Pass
47 | Large Bndle and save | LBS26.01 |  |  | No Run
48 | Large Bndle and save | LBS26.02 | Puneet | 2015-08-13 | Pass
49 | Large Bndle and save | LBS26.03 | Puneet | 2015-08-13 | Pass
50 | Large Bndle and save | LBS26.04 | Puneet | 2015-08-14 | Pass
51 | Large Bndle and save | LBS26.05 | Puneet | 2015-08-14 | Pass
52 | Large Bndle and save | LBS26.06 | Puneet | 2015-08-14 | Pass
53 | Large Bndle and save | LBS26.07 | Puneet | 2015-08-14 | Pass
54 | Large Bndle and save | LBS26.08 | Puneet | 2015-08-13 | Pass
55 | Large Bndle and save | LBS26.09 | Puneet | 2015-08-17 | Pass
56 | Large Bndle and save | LBS26.10 | Puneet | 2015-08-17 | Pass
57 | Large Bndle and save | LBS26.11 | Puneet | 2015-08-17 | Pass
58 | Large Bndle and save | LBS26.12 | Puneet | 2015-08-17 | Pass
59 | Large Bndle and save | LBS26.13 | Puneet | 2015-08-17 | Pass
|  | Total | 59
|  | Pass | 57
|  | Fail | 1
|  | NoRun | 1
|  | Blocked | 0
|  | In Progress | 0
|  | Deferred | 0

## CW New changes
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Copywriter | CW1.1 | Kamal | 2015-08-19 | Fail |  |  |  |  | CCM defect Id 37912
2 | Copywriter | CW2.1 | Kamal | 2015-08-19 | Fail |  |  |  |  | CCM defect Id 37917
3 | Copywriter | CW3.1 | Kamal | 2015-08-19 | Fail |  |  |  |  | CCM defect Id 37923
4 | Copywriter | CW4.1 | Priyabrat | 2015-08-19 | Pass
5 | Copywriter | CW4.2 | Priyabrat | 2015-08-19 | Pass
6 | Copywriter | CW4.3 | Priyabrat | 2015-08-25 | Pass |  |  |  |  | CCM 37924
7 | Copywriter | CW4.4 | Priyabrat | 2015-08-25 | Pass
8 | Copywriter | CW4.5 | Priyabrat | 2015-08-25 | Pass
9 | Copywriter | CW4.6 | Priyabrat | 2015-08-25 | Pass
10 | Copywriter | CW4.7 | Priyabrat | 2015-08-25 | Pass
11 | Copywriter | CW4.8 | Priyabrat | 2015-08-25 | Fail |  |  |  |  | CCM 38283
12 | Copywriter | CW4.9 |  |  | Blocked |  |  |  |  | CCM 38283
13 | Copywriter | CW4.10 |  |  | Blocked |  |  |  |  | CCM 38283
14 | Copywriter | CW4.11 | Kamal | 2015-08-26 | Fail |  |  |  |  | CCM 38336
15 | Copywriter | CW4.12 | Kamal | 2015-08-26 | Blocked |  |  |  |  | CCM 38336
16 | Copywriter | CW4.13 |  |  | No Run
17 | Copywriter | CW4.14 |  |  | No Run
18 | Copywriter | CW4.15 |  |  | No Run
19 | Copywriter | CW4.16 |  |  | No Run
20 | Copywriter | CW4.17 |  |  | N/A |  |  | priyabrat8/25/2015: import for translation funtionality is not present for My mobile skus.So marking these scenarios as N¦A
21 | Copywriter | CW4.18 |  |  | N\A |  |  | priyabrat8/25/2015: Export for translation funtionality is not present for My mobile skus.So marking these scenarios as N¦A
22 | Copywriter | CW4.19 |  |  | N\A |  |  | priyabrat8/25/2015: import for translation funtionality is not present for My mobile skus.So marking these scenarios as N¦A
23 | Copywriter | CW4.20 |  |  | N\A |  |  | priyabrat8/25/2015: import for translation funtionality is not present for My mobile skus.So marking these scenarios as N¦A
24 | Copywriter | CW4.21 |  |  | N\A |  |  | priyabrat8/25/2015: import for translation funtionality is not present for My mobile skus.So marking these scenarios as N¦A
25 | Copywriter | CW4.22 | Priyabrat | 2015-08-25 | Fail | [6 empty] | CCM 38289
26 | Copywriter | CW5.1 |  |  | No Run
27 | Copywriter | CW5.2 |  |  | No Run
28 | Copywriter | CW5.3 |  |  | No Run
29 | Copywriter | CW6.1 | Kamal | 2015-08-26 | Fail | [6 empty] | CCM 38339
30 | Copywriter | CW6.2 |  |  | N/A
31 | Copywriter | CW6.3 |  |  | No Run
32 | Copywriter | CW6.4 |  |  | No Run
33 | Copywriter | CW6.5 |  |  | No Run
34 | Copywriter | CW6.6 |  |  | No Run
35 | Copywriter | CW6.7 |  |  | No Run
36 | Copywriter | CW6.8 |  |  | No Run
37 | Copywriter | CW7.1 | Puneet | 2015-08-24 | Pass
38 | Copywriter | CW7.2 | Puneet | 2015-08-24 | Pass
39 | Copywriter | CW7.3 | Puneet | 2015-08-18 | Pass
40 | Copywriter | CW7.4 | Puneet | 2015-08-18 | Pass
41 | Copywriter | CW7.5 | Puneet | 2015-08-18 | Pass
42 | Copywriter | CW7.6 | Puneet | 2015-08-18 | Pass
43 | Copywriter | CW7.7 | Puneet | 2015-08-19 | Blocked |  |  | Defect id:CCM37816
44 | Copywriter | CW7.8 | Puneet | 2015-08-19 | Pass
45 | Copywriter | CW7.9 | Puneet | 2015-08-19 | Pass
46 | Copywriter | CW7.10 | Puneet | 2015-08-19 | Pass
47 | Copywriter | CW7.11 | Puneet | 2015-08-19 | Fail |  |  | Defect id:CCM37922
48 | Copywriter | CW7.12 | Puneet | 2015-08-24 | Pass
49 | Copywriter | CW7.13 | Puneet | 2015-08-24 | Pass
50 | Copywriter | CW7.14 | Puneet | 2015-08-24 | Pass
51 | Copywriter | CW7.15 | Puneet | 2015-08-24 | Pass
52 | Copywriter | CW7.16 | Puneet | 2015-08-24 | Pass
53 | Copywriter | CW7.17 | Puneet | 2015-08-24 | Pass
54 | Copywriter | CW7.18 | Puneet | 2015-08-24 | Pass
55 | Copywriter | CW7.19 | Puneet | 2015-08-24 | Pass
56 | Copywriter | CW7.20 | Puneet | 2015-08-24 | Pass
57 | Copywriter | CW7.21 | Puneet | 2015-08-24 | Pass
58 | Copywriter | CW7.22 |  |  | No Run
59 | Copywriter | CW7.23 |  |  | No Run
60 | Copywriter | CW7.24 |  |  | No Run
61 | Copywriter | CW7.25 |  |  | No Run
62 | Copywriter | CW7.26 |  |  | No Run
63 | Copywriter | CW7.27 | Puneet | 2015-08-19 | Pass
64 | Copywriter | CW7.28 | Puneet | 2015-08-19 | Pass
65 | Copywriter | CW7.29 | Puneet | 2015-08-19 | Pass
66 | Copywriter | CW7.30 | Puneet | 2015-08-19 | Pass
67 | Copywriter | CW7.31 | Puneet | 2015-08-18 | Fail |  |  | Defect id:CCM37816
68 | Copywriter | CW7.32 | Puneet | 2015-08-18 | Blocked |  |  | Defect id:CCM37816
69 | Copywriter | CW7.33 | Puneet | 2015-08-18 | Blocked |  |  | Defect id:CCM37816
70 | Copywriter | CW7.34 | Puneet | 2015-08-19 | Blocked |  |  | Defect id:CCM37816
71 | Copywriter | CW7.35 | Puneet | 2015-08-19 | Blocked |  |  | Defect id:CCM37816
72 | Copywriter | CW7.36 | Puneet | 2015-08-19 | Blocked |  |  | Defect id:CCM37816
73 | Copywriter | CW7.37 | Puneet | 2015-08-19 | Pass
74 | Copywriter | CW7.38 | Puneet | 2015-08-19 | Pass
75 | Copywriter | CW7.39 | Puneet | 2015-08-19 | Pass
76 | Copywriter | CW7.40 | Puneet | 2015-08-19 | Pass
77 | Copywriter | CW7.41 | Puneet | 2015-08-19 | Pass
78 | Copywriter | CW7.42 | Puneet | 2015-08-19 | Pass
79 | Copywriter | CW7.43 | Puneet | 2015-08-19 | Pass
80 | Copywriter | CW7.44 | Puneet | 2015-08-19 | Fail |  |  | Defect id:CCM37907
81 | Copywriter | CW7.45 | Puneet | 2015-08-19 | Blocked |  |  | Defect id:CCM37907
82 | Copywriter | CW7.46 | Puneet | 2015-08-19 | Pass |  |  | Defect id:CCM37889
83 | Copywriter | CW7.47 | Puneet | 2015-08-19 | Pass |  |  | Defect id:CCM37889
84 | Copywriter | CW7.48 | Puneet | 2015-08-19 | Pass |  |  | Defect id:CCM37892
85 | Copywriter | CW7.49 | Puneet | 2015-08-19 | Pass |  |  | Defect id:CCM37892
86 | Copywriter | CW7.50 | Puneet | 2015-08-19 | Pass
87 | Copywriter | CW7.51 | Puneet | 2015-08-19 | Blocked
88 | Copywriter | CW8.1 | Kamal | 2015-08-18 | Pass
89 | Copywriter | CW8.2 | Kamal | 2015-08-18 | Pass
90 | Copywriter | CW8.3 | Kamal | 2015-08-18 | Pass
91 | Copywriter | CW8.4 | Kamal | 2015-08-18 | Pass
92 | Copywriter | CW8.5 | Kamal | 2015-08-18 | Pass
93 | Copywriter | CW8.6 | Kamal | 2015-08-18 | Pass
94 | Copywriter | CW8.7 | Kamal | 2015-08-18 | Pass
95 | Copywriter | CW8.8 | Kamal | 2015-08-18 | Pass
96 | Copywriter | CW8.9 | Kamal | 2015-08-18 | Pass
97 | Copywriter | CW8.10 | Kamal | 2015-08-19 | Fail |  |  | CCM Defect_Id 37895
98 | Copywriter | CW8.11 | Kamal | 2015-08-19 | Fail |  |  | CCM Defect_Id 37895
99 | Copywriter | CW8.12 | Kamal | 2015-08-18 | Pass
100 | Copywriter | CW8.13 | Kamal | 2015-08-18 | Pass
101 | Copywriter | CW8.14 | Kamal | 2015-08-19 | Pass
102 | Copywriter | CW8.15 | Kamal | 2015-08-19 | Fail |  |  | CCM Defect_Id 37908
103 | Copywriter | CW8.16 | Kamal | 2015-08-19 | Pass
104 | Copywriter | CW8.17 | Kamal | 2015-08-18 | Pass
105 | Copywriter | CW8.18 | Kamal | 2015-08-19 | Pass
106 | Copywriter | CW8.19 | Kamal | 2015-08-19 | Pass
107 | Copywriter | CW8.20 | Kamal | 2015-08-19 | Pass
108 | Copywriter | CW8.21 | Kamal | 2015-08-19 | Pass
109 | Copywriter | CW8.22 | Kamal | 2015-08-19 | Pass
110 | Copywriter | CW8.23 | Kamal | 2015-08-18 | Pass
111 | Copywriter | CW8.24 | Kamal | 2015-08-19 | Pass
112 | Copywriter | CW8.25 | Kamal | 2015-08-19 | Pass
113 | Copywriter | CW8.26 | Kamal | 2015-08-19 | Pass
114 | Copywriter | CW8.27 | Kamal | 2015-08-19 | Pass
|  | Total | 108
|  | Pass | 66
|  | Fail | 13
|  | NoRun | 18
|  | Blocked | 11
|  | In Progress | 0
|  | Deferred | 0

## Store UI New changes
S. NO. | FUNCTIONAL AREA | TEST CONDITION ID | TESTER | EXECUTION DATE | STATUS | PASS | Screenshots | COMMENTS | BUILD TESTED | OPEN DEFECTS | CLOSED DEFECTS
1 | Store UI | SUI1.1 | Kamal | 2015-08-27 | Fail | 1 |  | Clarification has been logged in clarification log. Step:35 |  | CCM 38452
2 | Store UI | SUI1.2 | Kamal | 2015-08-27 | Blocked | 1 |  | Clarification has been logged in clarification log. Step:35 |  | CCM 38452
3 | Store UI | SUI2.1 |  |  | No Run | 1 |  | Scenario related to Corporate group
4 | Store UI | SUI2.2 | Kamal | 2015-08-25 | Pass | 1
5 | Store UI | SUI3.1 | Kamal | 2015-08-25 | Pass | 1
6 | Store UI | SUI3.2 | Kamal | 2015-08-25 | Pass | 1
7 | Store UI | SUI4.1 |  |  | No Run | 1 |  | Clarification has been logged in clarification log. Step:37
8 | Store UI | SUI4.2 | Kamal | 2015-08-26 | Pass | 1
9 | Store UI | SUI4.3 | Kamal | 2015-08-26 | Pass | 1
|  | Total | 9
|  | Pass | 5
|  | Fail | 1
|  | NoRun | 2
|  | Blocked | 1
|  | In Progress | 0
|  | Deferred | 0